## Capex Tracker
Project Name | Community | Category | Budget (CAD) | YTD Spend (CAD) | PO Status | % Complete | Notes
Boiler replacement | Aspen Ridge | WT-managed | 95000 | 76000 | PO issued | 80 | On track. Completion expected mid-May 2026. Two final commissioning steps remain.
AL dining wing wall removal | Aspen Ridge | OPT-managed | 42000 | 41200 | Closed | 100 | Project complete. Residents and care staff positive on outcome.
HVAC repair — IL east wing | Inglewood | OPT-managed | 42000 | 38000 | Closed | 100 | Came in $4K under budget. No service interruption.
Generator installation | Meadowlands | WT-managed | 78000 | 78000 | Closed | 100 | Commissioned April 22. Power resilience materially improved going into wildfire season.
Roof patching — Parkwood | Parkwood Place | WT-managed | 32000 | 0 | Quotes received | 0 | Two areas identified during April inspection. Work scheduled for June.
Bistro fit-out | Parkwood Place | OPT-managed | 56000 | 52000 | PO issued | 95 | Pilot launched mid-April. Strong early uptake. Final fixtures arriving early May.
MC wing renovation Phase 1 | The Kensington Victoria | OPT-managed | 145000 | 142000 | Closed | 100 | Two private rooms converted to companion suites. Phase 2 scoped for Q3.
Generator service contract | The Kensington Victoria | WT-managed | 18000 | 18000 | Closed | 100 | Annual maintenance complete.
Suite refresh program (rolling) | Portfolio | OPT-managed | 240000 | 168000 | PO issued | 70 | Targeted suite refreshes between move-outs and move-ins. 14 suites refreshed YTD.